## Disaster Recovery Checklist
Disaster Recovery Checklist: Ensuring Business Continuity in Times of Crisis |  |  |  | #VALUE!
This comprehensive disaster recovery checklist is designed to assist organizations in preparing for and responding to various types of disasters, such as cyber-attacks, system failures or natural disasters. The checklist outlines essential steps and considerations to minimize downtime, protect critical data and assets, and ensure the swift recovery of business operations. By following this checklist, businesses can enhance their resilience and maintain continuity during times of crisis, safeguarding their reputation, customer trust, and overall success.
How to use this checklist:
You can either work from this sheet or copy paste the tasks into your preferred project management tool. This tab (Disaster Recovery Checklist) gives you an overview of each task in your checklist. In each tab, you'll have a break down of subtasks and a progress tracker. Good luck!
Preparation | Data Backup and Storage | Infrastructure Protection | Communication and Notification | Recovery and Testing | Future-proofing
Assess potential risks and vulnerabilities to the business | Regularly backup all essential data, including files, databases and applications | Implement a robust cybersecurity measures, including firewalls, antivirus software and intrusion detection systems | Maintain up-to-date contact information for employees, clients and vendors, and emergency services. | Develop Recovery Procedures | Document all aspects of the plan
Identify critical assets, systems and data that needs protection | Ensure backups are stored security both on-site, and off-site to protect against physical and cyber threats. We recommend the 3-2-1 strategy. | Secure physical infrastrcuture with measures such as surge protectors, uninterruptible power supplies (UPS) and climate control systems. This may be even more important if you are situated in an area that is prone to natural disasters or regular power cuts. | Establish communication protocols for notifying stakeholders about the status of operations during and after a disaster | Conduct regular testing and training | Implement Zero Trust principles
Develop a comprehensive disaster recovery plan outlining roles, responsibilities and procedures | Implement encryption and access controls to protect sensitive data during storage and transmission. If you are using Macrium Reflect, your data will be encrypted and protected by Macrium Image Guardian. | Regularly update and patch software and firmware to address known vulnerabilities and enhance security. | Test communication channels and procedures regularly to ensure they are function and reliable | Establish goals and regular reviews | Apply Cyber Security essentials
Establish communication channels and protocols for internal and external stakeholders during a disaster |  |  |  |  | Regular review and updates

## Preparation
Assess potential risks and vulnerabilities | Task | What to consider | Progress
| Create a risk assessment team | Identify key stakeholders across different departments to create a risk assessment team and lead the team to drive coordination and completion of tasks on time. | Not Started
| Define objectives | What is the scope of the risk assessment and what objectives will help determine its success? e.g different systems, processes and assets that need to be evaluated. Specific objectives might include identifying potential threats, prioritizing risks based on impact to the business or likelihood of occurrence. | Planning
| Gather information | If you have a business continuity plan, review the existing documentation. If you don’t yet have one yet, now would be a good time to document it. Consider the organization's infrastructure, systems, data storage locations, and operations. | In Progress
| Identify threats and vulnerabilities | Identify threats and vulnerabilities that could impact the organization's business operations. Think about external threats too such as natural disasters, as well as internal vulnerabilities such as outdated legacy systems or inadequate security controls. | Done
| Develop mitigation strategies | Develop mitigation strategies to manage high-priority risks. This would be a good time to identify preventative measures to reduce the likelihood of the risks occurring. | Blocked
| Assess impact and likelihood: | Assess the potential impact on business operations from the risks that you have identified, looking at probability and severity. | Not Started
Identify critical assets, systems and data that needs protection | Audit systems and inventory | Conduct an audit to identify and catalog all critical hardware, software, applications and data repositories. | Not Started
| Classify assets | Assess how critical each asset is based on its criticality to business continuity, regulatory and compliance and its impact on the organization's goals. | Not Started
| Risk prioritization | Prioritize assets based on which ones are the most critical to the organization's objectives and the impact on the organization if compromised. | Not Started
| Data mapping | Map how data flows throughout the organization, where it is stored, sensitive data and the potential points of vulnerability. | Not Started
Develop a comprehensive disaster recovery plan outlining roles, responsibilities and procedures | Define objectives | Define objectives for your disaster recovery plan. That may include things like creating a dedicated team, minimizing downtime, SLAs for time for recovery, protecting data integrity and updating security measures. | Not Started
| Roles and responsibilities | Clearly define roles and responsibilities for team members involved in disaster recovery such as incident response teams, IT personnel and senior management. | Not Started
| Procedures, testing and training. | Document procedures for responding to different types of disaster. It’s always good to schedule regular testing for your plan through drills, simulations and tabletop exercises. Provide your team with training on their roles and how to respond. | Not Started
Establish communication channels and protocols | Communication strategy | Develop a communication strategy outlining how information will be disseminated to internal and external stakeholders during a disaster. | Not Started
| Primary communication channels | Identify primary and backup communication channels, including email, phone, SMS, office instant messaging tools like Teams or Slack, and collaboration tools. Define notification protocols for alerting stakeholders about the onset of a disaster, including escalation procedures and emergency contacts. | Not Started

## Data backup and storage
Regularly backup all essential data, including files, databases and applications | Task | What to consider | Progress
| Data Inventory | Conduct a comprehensive inventory of all essential data assets, including files, databases, and applications, across the organization. | Not Started
| Backup Schedule | Establish a regular backup schedule based on the criticality and frequency of changes to each data asset. | Not Started
| Backup Methods | Select appropriate backup methods and technologies based on the type of data and the organization's infrastructure. Options may include full backups, incremental backups, and differential backups. | Not Started
| Automated Backup Processes | Implement automated backup processes to ensure consistency, reliability, and efficiency in data backup operations. Leverage backup software solutions, such as Macrium Reflect, to automate scheduling, execution, and monitoring of backups. | Not Started
| Monitoring and Reporting | Implement ways to monitor and report the status and success of backups. | Not Started
Ensure Backups Are Stored Securely | 3-2-1 Backup Strategy | Adopt the 3-2-1 backup strategy, which involves maintaining at least three copies of data, stored on two different media types, with one copy stored off-site. This approach helps protect against various threats, including hardware failures, natural disasters, and cyberattacks. | Not Started
| Secure Storage Practices | Implement secure storage practices for both on-site and off-site backups. Use encryption to protect data at rest and during transmission. Implement access controls to restrict unauthorized access to backup repositories. | Not Started
| Off-Site Backup Locations | Identify secure off-site backup locations, such as cloud storage providers, data centers, or remote facilities, to store backup copies. Ensure that off-site backups are regularly updated and tested for recoverability. | Not Started
Implement Encryption and Access Controls: | Data Encryption | Implement encryption mechanisms to protect sensitive data both during storage and transmission. Utilize encryption algorithms and protocols to encrypt data at rest on backup media and in transit between backup systems. | Not Started
| Access Controls | Implement access controls to restrict access to backup repositories and ensure that only authorized personnel can view, modify, or delete backup data | Not Started
| Macrium Reflect Integration | If using Macrium Reflect for backup and disaster recovery, leverage built-in features such as Macrium Image Guardian to encrypt and protect backup images. Ensure that Image Guardian is configured to enforce encryption and access controls according to organizational security policies. | Not Started

## Communication and notification
Maintain up-to-date contact information for employees, clients and vendors, and emergency services | Task | What to consider | Progress
| Emergency Contact Lists | The emergency contact lists may be used for quick reference during crisis situations. Distribute these lists to key stakeholders and display them in prominent locations within the organization's facilities. | Not Started
Establish Communication Protocols | Notification procedures | Establish clear procedures for initiating and disseminating emergency notifications to employees, clients, vendors, and other stakeholders. Determine who has the authority to issue notifications and how they will be distributed across various communication channels. | Not Started
| Message Templates | Create message templates for different types of emergencies, such as natural disasters or cyberattacks. Customize these templates with relevant information and instructions before disseminating them to stakeholders. | Not Started
Test Communication Channels and Procedures | Scenario-Based Testing | Develop realistic scenarios that simulate various emergency situations and test the organization's ability to communicate effectively under pressure. Include scenarios that require coordination with external stakeholders, such as emergency responders or regulatory agencies. | Not Started
| Evaluation and Improvement | Evaluate the results of communication tests and exercises to identify strengths, weaknesses, and areas for improvement. Document lessons learned and update communication protocols accordingly to enhance preparedness for future emergencies. | Not Started

## Infrastructure Protection
Implement Robust Cybersecurity Measures | Task | What to consider | Progress
| Conduct a cybersecurity assessment | Conduct a comprehensive assessment of existing cybersecurity measures to identify gaps, weaknesses, and areas for improvement. | Not Started
| Implement cyber security and enhance protection | Implement advanced cybersecurity solutions to strengthen defenses against evolving threats. Consider deploying next-generation firewalls, endpoint detection and response (EDR) solutions, and threat intelligence platforms to detect and mitigate cyberattacks proactively. | Not Started
| Provide user training and awareness | Provide a training and awareness program to educate employees about cybersecurity best practices, such as recognizing phishing emails, using strong passwords, and avoiding suspicious websites. | Not Started
Secure Physical Infrastructure: | Conduct a physical security assessment | Conduct a physical security assessment to identify vulnerabilities in the organization's infrastructure, facilities, and equipment. Assess risks related to power surges, outages, climate control failures, and other potential threats. | Not Started
| Implement mitigation measures | Implement measures to secure physical infrastructure and minimize the risk of damage or disruption. Install surge protectors, uninterruptible power supplies (UPS), and climate control systems to safeguard critical equipment and maintain operational continuity. | Not Started
| Invest in backup power solutions | Consider investing in backup power solutions, such as generators or battery backups, to ensure continuous operation during power outages or emergencies. Develop contingency plans for managing power-related incidents and restoring operations promptly. | Not Started
Regularly Update and Patch Software | Establish a patch management process | Establish a formal patch management process to ensure that software and firmware are regularly updated to address known vulnerabilities and security flaws. | Not Started
| Conduct regular vulnerability scanning | Conduct regular vulnerability scans and assessments to identify outdated software, unpatched systems, and potential security weaknesses. Prioritize patching based on the severity of vulnerabilities and the criticality of affected systems. | Not Started

## Recovery and Testing
Develop Recovery Procedures | Task | What to consider | Progress
| Step by step process for restoring operations and systems | Develop a step by by step process for restoring operations and systems following a disaster, to ensure clarity and efficiency in recovery efforts. | Not Started
| Prioritize critical functions | Prioritize critical functions and services to reduce downtime and maintain essential business operations during a disaster | Not Started
Conduct regular testing and training: | Conduct testing and simulations | Conduct testing and simulations of the disaster recovery plan to identify weaknesses and areas for improvement | Not Started
| Provide training to team | Provide training to the team on best practices and equip them with the necessary tools, resources and documentation for disaster recovery including access to back up systems and communication channels. | Not Started
Establish goals and regular reviews: | Establish recovery objective | Establish recovery time objectives (RTO) and recovery point objectives (RPO) to guide the recovery process and measure success in restoring operations. | Not Started
| Schedule regular reviews | Schedule regular reviews of the disaster recovery plan based on success measures and learnings from testing, allowing for continuous improvement. | Not Started

## Future-proofing
Document all aspects of the disaster recovery plan | Task | What to consider | Progress
| Document disaster recovery plan | Document all aspects of the disaster recovery plan, including policies, procedures, configurations, and key contacts, ensuring clarity and accessibility for all team members. | Not Started
| Record incident responses | Keep records of past incidents, including the nature of the incident, responses taken, and lessons learned, to inform future preparedness efforts and improve response strategies. | Not Started
Implement Zero Trust principles | Apply Zero Trust principles | Identify areas where Zero Trust principles can be applied, such as user access controls, network segmentation, and data encryption. | Not Started
| Implement Zero Trust controls | Deploy multi-factor authentication (MFA) for all user accounts to enhance identity verification. Implement least privilege access policies to restrict user and system access based on specific roles and responsibilities. | Not Started
| Establish micro-segmentation | Establish micro-segmentation to isolate critical assets and limit lateral movement within the network. | Not Started
| Enable encryption | Enable encryption for data at rest and in transit to protect sensitive information from unauthorized access. | Not Started
Apply Cyber Security essentials | Regular patch and updates | Set up a schedule to update and patch all systems and software regularly to address known vulnerabilities and mitigate potential security risks. | Not Started
| Team training | Plan and coordinate security awareness training for employees to educate them about common cyber threats and best practices for data protection. | Not Started
| Antivirus, anti-malware, IDPS | Maintain up-to-date antivirus and anti-malware software on all devices to detect and prevent malicious attacks. Implement intrusion detection and prevention systems (IDPS) to monitor network traffic and detect suspicious activities. | Not Started
Regular review and updates | Schedule regular reviews of documentation | Schedule regular reviews of the disaster recovery documentation to ensure it remains accurate and up-to-date. Update the documentation to reflect changes in technology, regulations, and business requirements, maintaining its relevance and effectiveness over time. | Not Started